## Sheet1
BUG LIST
Bug ID | Module | Summary | Title / Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Screenshot
1. Login as error_user.
BUG-001 | Checkout | Last Name field validation error. | System rejects valid input for the Last Name | 2. Go to Checkout. | System should navigate to the | Error "Last Name is required" | High | High
|  |  | field under specific conditions. | 3. Fill all fields & click Continue. | Overview page. | is displayed.
1. Login as error_user.
BUG-002 | Checkout | Unresponsive Finish button. | Order completion is blocked for the error_user. | 2. Navigate to Overview page. | Should navigate to | Page does not redirect or | High | High
|  |  |  | 3. Click "Finish" button. | "Thank you for your order" page. | complete the order.
BUG-003 | Product | Broken product images. | Product images fail to load for specific user roles. | 1. Login as problem_user. | Each product should display | All products display the same | Medium | High
|  |  |  | 2. View product listing. | its unique image. | "dog" placeholder image.
1. Navigate to Login page.
BUG-004 | Product | Significant loading delay on product page. | The system experiences a 3-5 second lag | 2. Login as | The Inventory page should | Page remains blank/loading | Low | Medium
|  |  | when loading the inventory list for specific users. | performance_glitch_user. | load within 1 second. | for 3-5 seconds before
|  |  |  | 3. Observe the loading time |  | displaying items.
for the products.
1. Login as problem_user.
BUG-005 | Product | "Add to Cart" button failure for | The "Add to Cart" button is unresponsive | 2. Locate the "Sauce Labs | The item should be added to | The button is clickable but
|  | specific item. | specifically for the Sauce Labs Fleece Jacket | Fleece Jacket" in the inventory | the cart and the button text | nothing happens; the cart | Medium | Medium
|  |  | when using a specific user profile. | list. | should change to "Remove". | badge does not update.
3. Click the "Add to Cart" button.
BUG-006 | Product | Sorting functionality failure. | Price sorting does not update the UI for the | 1. Login as problem_user. | Products should sort by price | No change in the sorting order | Medium | Medium
|  |  | problem_user. | 2. Select "Price (High to Low)". | descending. | of the products.